SECTION 01 25 00 - SUBSTITUTION PROCEDURES

Revise this Section by deleting and inserting text to meet Project-specific requirements.

GENERAL

SUMMARY

Section includes administrative and procedural requirements for substitutions.

Related Requirements:

Retain subparagraph below to cross-reference requirements Contractor might expect to find in this Section but are specified in other Sections.

Section 016000 "Product Requirements" for requirements for submitting comparable product submittals for products by listed manufacturers.

DEFINITIONS

Retain terms that remain after this Section has been edited for a project.

Substitutions:  Changes in products, materials, equipment, and methods of construction from those required by the Contract Documents and proposed by Contractor.

ACTION SUBMITTALS

AIA Document A511 suggests adding requirements to AIA Document A201 in the Supplementary Conditions for consideration of requests received after Contract award.  "Substitution Requests" Paragraph below expands requirements suggested by AIA Document A511.

Substitution Requests:  Submit three copies of each request for consideration to Architect, Engineer, and Owner.  Identify product or fabrication or installation method to be replaced.  Include Specification Section number and title and Drawing numbers and titles.

If retaining last option in "Substitution Request Form" Subparagraph below, insert a sample of the form to be used in Project Manual.

Substitution Request Form:  Use CSI Form 13.1A.

Documentation:  Show compliance with requirements for substitutions and the following, as applicable:

Retain and revise requirements in first 13 subparagraphs below that are applicable and necessary and are not included in the Supplementary Conditions.

Statement indicating why specified product or fabrication or installation cannot be provided, if applicable.

Coordination information, including a list of changes or revisions needed to other parts of the Work and to construction performed by Owner and separate contractors, that will be necessary to accommodate proposed substitution.

Detailed comparison of significant qualities of proposed substitution with those of the Work specified.  Include annotated copy of applicable Specification Section.  Significant qualities may include attributes such as performance, weight, size, durability, visual effect, sustainable design characteristics, warranties, and specific features and requirements indicated.  Indicate deviations, if any, from the Work specified.

Product Data, including drawings and descriptions of products and fabrication and installation procedures.

Samples, where applicable or requested.

Certificates and qualification data, where applicable or requested.

List of similar installations for completed projects with project names and addresses and names and addresses of architects and owners.

Material test reports from a qualified testing agency indicating and interpreting test results for compliance with requirements indicated.

Research reports evidencing compliance with building code in effect for Project, from ICC-ES or applicable authority having jurisdiction.

Detailed comparison of Contractor's construction schedule using proposed substitution with products specified for the Work, including effect on the overall Contract Time.  If specified product or method of construction cannot be provided within the Contract Time, include letter from manufacturer, on manufacturer's letterhead, stating date of receipt of purchase order, lack of availability, or delays in delivery.

Cost information, including a proposal of change, if any, in the Contract Sum.

Contractor's certification that proposed substitution complies with requirements in the Contract Documents except as indicated in substitution request, is compatible with related materials, and is appropriate for applications indicated.

Contractor's waiver of rights to additional payment or time that may subsequently become necessary because of failure of proposed substitution to produce indicated results.

Architect's Action:  If necessary, Architect or Owner will request additional information or documentation for evaluation within seven days of receipt of a request for substitution.  Architect will notify Owner and Contractor of acceptance or rejection of proposed substitution within 15 days of receipt of request, or seven days of receipt of additional information or documentation, whichever is later.

Owner Acceptance:  Owner reserves the right to reject substitution requests, regardless of acceptance by Architect.

Forms of Acceptance:  Change Order, Construction Change Directive, or Architect's Supplemental Instructions for minor changes in the Work.

Use product specified if Architect does not issue a decision on use of a proposed substitution within time allocated.

QUALITY ASSURANCE

Compatibility of Substitutions:  Investigate and document compatibility of proposed substitution with related products and materials.  Engage a qualified testing agency to perform compatibility tests recommended by manufacturers.

PRODUCTS

SUBSTITUTIONS

Review this article with Owner to confirm what is considered a substitution by Owner and to coordinate Owner's role in approving substitutions.  If substitution requests are restricted to before bid opening, include requirements in the Instructions to Bidders.

Substitutions for Cause:  Submit requests for substitution immediately on discovery of need for change, but not later than 15 days prior to time required for preparation and review of related submittals.

Conditions:  Architect will consider Contractor's request for substitution when the following conditions are satisfied:

Revise conditions in subparagraphs below.  If required, insert more restrictive conditions to limit consideration of proposed substitutions.

Requested substitution is consistent with the Contract Documents and will produce indicated results.

Requested substitution provides sustainable design characteristics that specified product provided.

Requested substitution will not adversely affect Contractor's construction schedule.

Requested substitution has received necessary approvals of authorities having jurisdiction.

Requested substitution is compatible with other portions of the Work.

Requested substitution has been coordinated with other portions of the Work.

Requested substitution provides specified warranty.

If requested substitution involves more than one contractor, requested substitution has been coordinated with other portions of the Work, is uniform and consistent, is compatible with other products, and is acceptable to all contractors involved.

Substitutions for Convenience:  Not allowed.

EXECUTION (Not Used)

END OF SECTION 01 25 00